## How to fill it
02_sizing — how to fill it in (Assignment 2)
WHICH PROJECT IS THIS ABOUT?
Your team's own project: the customer-support agent your team chose for the course (one of the proposals P1–P8 in the project document, or your own idea). One sheet per team, committed as 02_sizing.xlsx in your Git repository. It is NOT about Paylio: Paylio is the fictional company of the in-class exercise; it only appears in column H of the Inputs tab, to show what a filled-in cell looks like.
WHAT THE SHEET ANSWERS
Is your agent worth building for the company? You get: the net value per year in three scenarios (pessimistic, base, optimistic), an expected value, the comparison with doing nothing and with another project the same team could do, a decision (go / no-go / conditional go), the one assumption that flips the decision, and a build / buy / orchestrate score. Your memo (02_investment_memo.md) explains these numbers in one page.
WHERE YOUR NUMBERS COME FROM
1) Your company's numbers are in your proposal (table at the bottom of this tab): treat them as measured — they are your company's logs. 2) Orders of magnitude from the Session 2 slides (a human ticket costs €5–15 all-in; an LLM conversation €0.02–0.20): analogy. 3) Everything else is your estimate: write guess, and say in the note how you would check it. Every yellow cell gets a source type and a note.
STEP BY STEP — about one hour, as a team. Type only in the yellow cells.
Step | Where | What to enter | Tip
1 · Volume and human cost | Inputs, rows 6–9 | Tickets per month; number of support agents; what ONE agent costs the company per year (all-in); the cost of one ticket handled by a human. | From your proposal. Row 10 gives the agent time per ticket from headcount (Paylio: 60 × €45k ÷ 480,000 ≈ €5.6; €10 all-in with team leads, QA and tools); row 11 the tickets per agent per day.
2 · Your categories | Inputs, A14:A16 and rows 14–16 | Rename the three categories of work your agent deals with — ticket types, requests, incidents, accounts (e.g. P4: refund requests, delivery questions, account issues) — and give each one's share of the volume. | Fewer than three? Set Include = 0 (rows 34–36) for the unused ones.
3 · Automatable share | Inputs, rows 18–20 | In each category, the share of tickets the agent could handle at all (answerable from the documentation, the policy, the data it can see). | Guess from a sample of tickets — and say how you would check it.
4 · Deflection realised | Inputs, rows 22–24 | Of those, the share actually resolved without a human once live. | Usually THE assumption that flips the decision: mark it “guess → S4 test”.
5 · Errors and what they cost | Inputs, rows 26–32 | The error rate per category, and the cost in € of one wrong answer (customer retries, refund leakage, penalty, churn, a legal case). | The costly categories are where a human must stay — that is a scope decision (step 6).
6 · Scope | Inputs, rows 34–36 | 1 = the agent handles this category, 0 = it does not. | Try 0 on the riskiest category and watch the decision.
7 · Adoption by quarter | Inputs, rows 39–42 | The share of the deflectable volume actually handled in Q1, Q2, Q3, Q4. | Never 100 % in Q1 — Octopus Energy went from a handful of emails to 34 %, then 45 %.
8 · AI cost | Inputs, rows 45–46 | The AI cost per conversation (tokens × price) and the retry overhead. | €0.02–0.20 per conversation; recheck token prices the day you fill it in.
9 · Fixed costs | Inputs, rows 49–56 | Integration, evaluation, supervision (people in the loop, in FTE), monitoring and on-call, re-evaluation when the model changes. | The human in the loop is a cost line, not free.
10 · The two comparisons | Inputs, rows 59–60 | How much the current process improves each year on its own (do-nothing), and the yearly value of the next-best project the same team could do (name it in the note). | The hurdle is another project, not zero.
11 · Probabilities | Inputs, row 63 | How likely you find the pessimistic, base and optimistic scenarios. | Must sum to 1 (row 64 checks it).
12 · Read the result | Decision tab | Net value per scenario, expected value, comparisons, the decision cell, and the sensitivity table: the deflection rate at which the decision flips. | Do not type here. The flip point goes in the memo — your Session 4 prototype will measure it.
13 · Build, buy or orchestrate | Build or buy tab | Weights (sum 100 %) and a score from 1 to 5 for each option on the ten questions; the vendor's price per resolution for the break-even. | The score informs the decision; the memo makes it.
14 · Write the memo | 02_investment_memo.md | Recommendation on line one, the four CFO questions, one line on build / buy / orchestrate. | Same base case as this sheet.
STARTING NUMBERS FROM THE PROJECT DOCUMENT
Proposal | Company numbers | The pain | Kind of value
P1 · HR & payroll SaaS | 2,500 customer companies · 40,000 tickets/month · 60 support agents | 55 % of tickets are “how do I…” questions already answered in the documentation; peaks at month end | Work avoided
P2 · B2B payments fintech | 800 merchants · 12,000 tickets/month | Agents spend 40 % of handling time reading transaction history and past tickets | Time saved (copilot)
P3 · DevOps / observability | 5,000 accounts · tickets ×10 during incidents (normal volume not given: estimate it) | During an outage, 70 % of tickets say the same thing | Incident load — tickets per incident × incidents a year
P4 · E-commerce logistics | 15,000 merchants · 25,000 tickets/month | 30 % of tickets are label refunds; refunds under €20 cost more to process than they are worth | Work avoided; the cost of error is refund leakage
P5 · Ed-tech LMS | 14 countries · 6 languages · 20 agents (volume not given: estimate it) | Tickets in Portuguese, Polish, Arabic wait 2–3× longer | Work avoided — use the categories for languages
P6 · Project-management SaaS | 30,000 SMB accounts · 9,000 tickets/month · 8 % annual churn | Churn signals visible in support weeks before cancellation | Work avoided + revenue retained (Other value)
P7 · Cybersecurity SaaS | 400 enterprise accounts · 6,000 tickets/month · 25 engineers · SLA P1 = 1 h, P2 = 4 h | Misprioritised tickets cause SLA breaches and penalties | Time saved + penalties avoided (Other value)
P8 · Hospitality-tech | 3,000 hotels (volume not given: estimate it) · reviews.csv for real data | 20 % of tickets are analysis requests; answer today in 4 days | Time saved — analysis requests answered faster
Own project | The numbers of your 00_pitch.md | Your pain, expressed as a cost | Pick the kind of value below; invent plausible numbers and label them
NOT ONLY TICKETS — OTHER KINDS OF VALUE, WITH WORKED EXAMPLES
Every agent is sized the same way: volume × share in scope × success rate × value per success − AI cost − cost of errors − fixed costs. Only the unit and the value change. Pick the line that matches your agent (you can combine two). Numbers below are illustrative — replace them with yours.
Kind of value | Typical for | What goes where in the sheet | Illustrative example
Work avoided (deflection) | P1, P4, P5 | Volume = tickets · success rate = deflection · value per unit = human cost of one ticket. | P1: 40,000 tickets × 55 % “how do I” × 68 % automatable × your deflection rate (say 50 %) × €10 ≈ €75k a month at full adoption.
Time saved (copilot) | P2, P7 (triage), P8 | Volume = tickets or requests the agent helps with · success rate = share of handling time saved · value per unit = human cost of one. | P2: 12,000 tickets × 100 % with the copilot × 20 % of time saved × €10 ≈ €24k a month.
Revenue retained | P6 | Use an Other value row (67–68): accounts at risk that reach support × share saved × yearly revenue per account. | P6: 30,000 accounts × 8 % churn = 2,400 lost a year; half open a ticket first; 10 % saved = 120 × €1,200 ≈ €144k a year.
Penalties avoided | P7 | Use an Other value row: breaches a year × share avoided × penalty per breach (from the contracts). | P7: 240 SLA breaches a year × 30 % avoided × €2,000 ≈ €144k a year.
Faster answers, incident load | P3, P8 | Volume = requests or incident tickets (incidents a year × tickets per incident ÷ 12) · value = agent time per ticket; the speed gain goes in the memo. | P3: 20 incidents a year × 1,500 tickets each ÷ 12 = 2,500 tickets a month.
Data & AI Product: From Diagnosis to Delivery · Albert School MSA-DAT07-04 · Assignment 2 · BleuAI

## Inputs
02_sizing — your agent · Inputs
Keelpay copilot (routing + drafting) - sizing built bottom-up from the frozen brief in the README. 'Low' = pessimistic, 'High' = optimistic. Yellow = input; green font = link to the Flow tab, where time saved, error and AI costs are derived. Time-saved kind of value: the 'success rate' is the share of handling time saved, applied to every ticket the copilot handles.
Parameter | Unit | Low (pessimistic) | Base | High (optimistic) | Source type | Note / where the number comes from
VOLUME AND HUMAN COST
Volume per month (tickets, requests, conversations…) | tickets | 20000 | 20500 | 21000 | given | Scenario data (README): ~20,000 tickets a month today. Base and High add the average year-1 effect of merchant growth (about +5% / +10% by year end); the do-nothing text in 01 says volume grows.
Tier-1 support agents (headcount) | people | 25 | 25 | 25 | guess | 20,000 tickets x ~10 min hands-on / ~130 productive hours per agent. Test: headcount and timesheets of a real support team.
Cost of ONE agent to the company per year (all-in) | € / year | 50000 | 50000 | 50000 | guess | All-in yearly cost of a customer adviser in France. Analogy to check: job postings (France Travail, Michael Page) plus employer charges. Source it on the day.
Cost of ONE unit handled by a human (ticket, request…) | € / ticket | 6 | 7 | 8 | analogy | Course order of magnitude: a human ticket costs EUR 5-15 all-in (S2 slides). Base 7 = agent time (row 10, ~5.2) x ~1.35 for the part of team leads, QA and tools that scales with agent time.
Check — cost per ticket from headcount, base = agents × cost per agent ÷ tickets per year | € / ticket |  |  |  |  | Formula, not an input: agents × cost per agent ÷ (volume × 12) = the agent time per unit. Row 9 should be equal or higher (Paylio: €5.6 of agent time, €10 all-in).
Check — tickets per agent per working day, base (21 working days a month) | tickets |  |  |  |  | Formula, not an input: volume ÷ agents ÷ 21 — a sanity check (Paylio ≈ 32 tickets a day).
TICKET CATEGORIES
Share of the volume by category (rename the three categories in A14:A16 — the other blocks follow)
Payment status and payouts | share | 45% | 45% | 45% | guess | Share of tickets by type. Test: category tags in the helpdesk over three months.
Disputes and chargebacks | share | 20% | 20% | 20% | guess | Same test. Disputes are the costly category (deadlines).
Technical / API and compliance | share | 35% | 35% | 35% | guess | Same test.
Automatable share (answerable from documentation)
| share | 100% | 100% | 100% | decision | The copilot reads and routes every ticket, so every ticket is in the base for time saved.
| share | 100% | 100% | 100% | decision | The copilot reads and routes every ticket, so every ticket is in the base for time saved.
| share | 100% | 100% | 100% | decision | The copilot reads and routes every ticket, so every ticket is in the base for time saved.
Success rate on the automatable share (deflection — or share of time saved, see the guide)
| share |  |  |  | guess | Share of handling time saved = routing slice + drafting slice, derived on the Flow tab. THE assumption that flips the decision: test on the S4 prototype and the S6 A/B.
| share |  |  |  | guess | Share of handling time saved = routing slice + drafting slice, derived on the Flow tab. THE assumption that flips the decision: test on the S4 prototype and the S6 A/B.
| share |  |  |  | guess | Share of handling time saved = routing slice + drafting slice, derived on the Flow tab. THE assumption that flips the decision: test on the S4 prototype and the S6 A/B.
Error rate — share of AI answers that are wrong
| share |  |  |  | guess | Uncaught serious errors per ticket handled (Flow tab) divided by the share of time saved, because the template applies error cost to time-saved-equivalent tickets.
| share |  |  |  | guess | Uncaught serious errors per ticket handled (Flow tab) divided by the share of time saved, because the template applies error cost to time-saved-equivalent tickets.
| share |  |  |  | guess | Uncaught serious errors per ticket handled (Flow tab) divided by the share of time saved, because the template applies error cost to time-saved-equivalent tickets.
Cost of one wrong answer
| € / error | 200 | 150 | 120 | guess | Wrong payment reply or ticket stuck in the wrong desk: extra contacts, goodwill credit, churn tail. Pessimistic is higher.
| € / error | 600 | 400 | 300 | guess | Missed chargeback deadline or wrong amount told: chargeback fees (analogy: Mastercard 2025, $128 per chargeback) plus lost dispute plus complaint risk.
| € / error | 450 | 300 | 250 | guess | Missed compliance hold or API incident handled late: regulatory exposure, merchant churn. Legal/reputational line (see governance).
Include category in scope? (1 = yes, 0 = no)
| 1/0 | 1 | 1 | 1 | decision | Scope decision. Try 0 on disputes and watch the decision.
| 1/0 | 1 | 1 | 1 | decision | Scope decision. Try 0 on disputes and watch the decision.
| 1/0 | 1 | 1 | 1 | decision | Scope decision. Try 0 on disputes and watch the decision.
ADOPTION RAMP — share of deflectable volume actually handled, by quarter
Q1 | share | 5% | 15% | 25% | guess | Pessimistic = the guardrail fails and the rollout stops at about 10% (S4/Q1 gate), not a world with heavy errors and full ramp. Staged rollout: routing starts on low-critical tickets, each step conditional on a guardrail holding (template: staged like Octopus Energy).
Q2 | share | 10% | 35% | 50% | guess | staged like Octopus Energy (a handful → 34 % → 45 %); each step conditional on a guardrail holding
Q3 | share | 10% | 55% | 70% | guess | staged like Octopus Energy (a handful → 34 % → 45 %); each step conditional on a guardrail holding
Q4 | share | 10% | 70% | 85% | guess | staged like Octopus Energy (a handful → 34 % → 45 %); each step conditional on a guardrail holding
AI HANDLING COST
AI cost per time-saved-equivalent ticket (tokens, inference) | € / conv. |  |  |  | guess | AI cost per ticket handled (Flow tab, routing call + draft with retrieval) divided by the share of time saved. Course order of magnitude: EUR 0.02-0.20 per conversation. Recheck token prices the day you fill it in.
Retry / escalation overhead | × | 1.5 | 1.3 | 1.2 | guess | Retries and second drafts after a reroute still cost tokens.
FIXED AND SEMI-FIXED COSTS
Integration (CRM, knowledge base, auth, logging) — one-off | € | 110000 | 80000 | 60000 | guess | Helpdesk and ledger integration, retrieval over desk policies, routing table, logging, review screen. Internal estimate; get a quote.
Amortisation period | years | 3 | 3 | 3 | decision
Evaluation — eval-set upkeep and human graders | € / year | 25000 | 15000 | 12000 | guess | Gold set upkeep, labelling by a second person, per-step evaluation.
Quality owner - sampling audits, thresholds, upkeep | FTE | 0.75 | 0.5 | 0.35 | guess | Quality owner: sampling audits of auto-routed tickets, threshold tuning, prompt and table upkeep. Support agents' own triage and review time is already in handling time.
Cost per supervision FTE | € / year | 60000 | 60000 | 60000 | guess | Loaded cost of a qualified analyst; check against the agent cost in row 8.
Monitoring and on-call | € / year | 40000 | 20000 | 12000 | guess | Mostly people time for monitoring and on-call. Hosting of the two endpoints in our own cloud (router and drafter, scale to zero, see Read options tab) is about EUR 2-3k a year. Data constraint: no external model API (README).
Model-version changes per year | changes | 4 | 3 | 2 | guess | Each model, prompt or table change replays the gold set (S7 trigger).
Re-evaluation cost per model change | € / change | 4000 | 3000 | 3000 | guess
THE TWO COMPARISONS
Do-nothing: yearly efficiency gain of the current process | share | 2% | 3% | 5% | analogy | Agents get faster with experience and macros. The course class case uses 5% as the top of the range; base lower because our team has no stated tooling change.
Next-best project — net annual value (the hurdle) | € / year |  |  |  | guess | Next-best project: rules-only ticket-to-transaction attach plus routing on structured fields, no AI (value derived on the Flow tab). Name: 'rules-only attach'.
SCENARIO PROBABILITIES
Probability of each scenario | p | 0.3 | 0.5 | 0.2 | judgement | Our reading of the scenarios; must sum to 1.
Check — probabilities sum to 1 | [5 empty] | formula
OTHER VALUE — when your agent creates value beyond the work it removes (revenue retained, penalties avoided, sales…)
Other value 1 - hand-overs avoided (misrouted tickets) | € / yr |  |  |  | guess | Misroute rate falls from 1 in 7 (given) to 12% / 10% / 8% on tickets the copilot handles, x cost of a hand-over x adoption (Flow tab).
Other value 2 — rename (e.g. SLA penalties avoided) | € / yr |  |  |  |  | Not used. Missed-deadline penalties avoided are not valued here: no contract data in the scenario (see memo).
Sources: README frozen brief (given figures). Course S2 slides (human ticket EUR 5-15; AI conversation EUR 0.02-0.20; do-nothing 5%). Brynjolfsson, Li & Raymond, 'Generative AI at Work', QJE 140(2), 2025 (about -13% time per issue). Mastercard 2025 chargeback cost ($128). Job postings for customer advisers in France (France Travail, Michael Page, 2026) - to be re-sourced on the day. Token and GPU prices on the Read options tab are guesses to recheck.

## Flow
02_sizing - Flow: how the inputs are derived (routing + drafting)
Yellow = input (Low = pessimistic, High = optimistic). Black = formula. Rows 15, 24, 30 and 35 feed the Inputs tab.
Line | Unit | Low | Base | High | Source type | Note / test
SUB-CASE A - ROUTING (read the message, route the ticket)
Share of handling time: reading and routing | share | 15% | 15% | 15% | given | README frozen brief.
Share of tickets routed automatically (clear and not critical) | share | 35% | 55% | 70% | guess | The rest goes to human triage. Test: gold set at several thresholds (S4).
Cut in reading and routing time on those tickets | share | 50% | 65% | 80% | guess | The agent no longer reads for routing, but still sees the case. Test: time study with and without (S5).
Time saved by A (share of total handling time) | share |  |  |  | formula | Slice x auto-lane share x cut. Triage tickets save nothing here (conservative).
SUB-CASE B - DRAFTING (find the payment and history, write the reply)
Share of handling time: finding the payment and history, and writing | share | 45% | 45% | 45% | given | README frozen brief.
Cut in that time with a cited draft | share | 12% | 22% | 30% | analogy | Published gain is about -13% time per issue overall (Brynjolfsson et al., QJE 2025) on all work; this slice is where a draft acts, so a larger cut here. Test: S5/S6.
Share of tickets correctly routed (the draft is usable) | share | 88% | 92% | 95% | guess | Today 6 in 7 (86%, given). The copilot improves it; a misrouted ticket gets a draft for the wrong desk and no saving.
Time saved by B (share of total handling time) | share |  |  |  | formula | Slice x cut x correctly routed share.
TOTAL time saved at full adoption (share of handling time) | share |  |  |  | formula | Feeds Inputs rows 22-24. Cross-check: published about 13%; the course's own P2 example uses 20%.
ERRORS AND AI COST (per ticket the copilot handles)
Uncaught serious errors per ticket handled - payment status | share | 0.1% | 0.05% | 0.03% | guess | INCREMENTAL uncaught serious errors versus today (humans also misroute 1 in 7): auto-route error nobody catches, or wrong draft validated unread, with a real consequence. Test: seeded errors in S4 (hypothesis 4).
Uncaught serious errors per ticket handled - disputes | share | 0.25% | 0.12% | 0.07% | guess | Higher: deadlines and amounts.
Uncaught serious errors per ticket handled - technical / compliance | share | 0.15% | 0.08% | 0.05% | guess
AI cost per ticket handled - routing model call | EUR | 0.003 | 0.002 | 0.001 | guess | Self-hosted small model: marginal cost is near zero, the endpoint is a fixed cost (Read options tab).
AI cost per ticket handled - draft (retrieval, queries, generation) | EUR | 0.01 | 0.005 | 0.003 | guess | Self-hosted drafter: the marginal cost per ticket is near zero (retrieval, database queries, power); the endpoint is a fixed cost in Inputs row 54.
AI cost per ticket handled - total | EUR |  |  |  | formula | Feeds Inputs row 45.
OTHER VALUE - hand-overs avoided
Misroute rate today | share |  |  |  | given | 1 ticket in 7 first lands in the wrong desk (README).
Misroute rate on tickets the copilot handles | share |  |  |  | formula | Equal to 1 minus the correctly routed share of row 13. Test: reroute counts in S4 (gold set) then S6.
Cost of one hand-over | EUR | 2 | 3 | 4 | guess | Queue delay and merchant irritation only: the second desk re-reading is hands-on time already inside the 15% slice. Test: time study.
Year-1 adoption factor (average of the four quarters) | share |  |  |  | formula
Hand-overs avoided, year-1 value | EUR / yr |  |  |  | formula | Feeds Inputs row 67.
NEXT-BEST PROJECT - rules-only ticket-to-transaction attach and routing on structured fields (no AI)
Share of handling time saved | share | 3% | 6% | 9% | guess | Removes the search for the payment (about half of slice B) for tickets with an ID or amount, and routes the structured part. Test: observe 20 tickets.
Adoption factor | share | 60% | 70% | 80% | guess | A rule needs less ramp-up than a model, but it also has a build quarter.
Yearly cost (build amortised + upkeep) | EUR / yr | 35000 | 30000 | 25000 | guess | Integration is the same work as step 3 of the copilot, so it is not lost if the copilot is built later.
Net annual value of the next-best project | EUR / yr |  |  |  | formula | Feeds Inputs row 60 (the hurdle).

## Read options
02_sizing - Read options: monthly cost of the five ways to read a ticket (step 1)
All prices are guesses to recheck on the day. Effectiveness is NOT scored here: it is measured on the gold set in S4. This tab answers the cost and data-control criteria only.
ASSUMPTIONS
Tickets per month | tickets |  | given |  |  | Scenario data.
Input tokens per ticket (instructions, examples, message) | tokens | 1200 | guess |  |  | Prompted options need instructions and a few examples; the fine-tuned model needs far fewer.
Output tokens per ticket (the JSON) | tokens | 150 | guess
API price, small model - input | EUR / M tokens | 0.15 | guess |  |  | Recheck on the provider's price page the day you use it.
API price, small model - output | EUR / M tokens | 0.6 | guess
API price, large model - input | EUR / M tokens | 3 | guess
API price, large model - output | EUR / M tokens | 15 | guess
Router endpoint in our cloud account - small fine-tuned model, CPU, scale to zero | EUR / month | 10 | guess |  |  | Container on Cloud Run with min-instances 0, billed per second, same pattern as the Museum Guide demo (free tier at its volume). 20,000 tickets x ~4 s x 2 vCPU is about 160k vCPU-seconds a month, around the free tier. Recheck the price list.
Fine-tuning runs per year | runs | 4 | guess |  |  | Initial training plus re-training when the gold set or taxonomy changes.
Cost of one fine-tuning run | EUR | 300 | guess |  |  | Small model, short run on a rented GPU. Does not include people time (that is in evaluation and supervision).
Larger open-source model (7-30B), prompted - drafter class, GPU scale to zero | EUR / month | 100 | guess |  |  | GPU billed per second, no always-on cost: tickets are processed asynchronously, so a cold start of tens of seconds is acceptable. About 20,000 x 15 s = 83 GPU-hours at roughly EUR 0.8-1 an hour. Recheck the price list.
Option |  | EUR / month | EUR / year | Tickets leave Keelpay? | Version pinned by us? | How it is computed / note
A - Deterministic rules |  | 20 |  | no | yes | Small service, mostly maintenance time (not counted).
B - Classical ML / small encoder |  | 60 |  | no | yes | CPU service; labelling effort sits in evaluation.
C - Open-source LLM, prompted, in our cloud account |  |  |  | no | yes | Larger model, bigger GPU than D.
D - Small fine-tuned LLM, in our cloud account |  |  |  | no | yes | Endpoint plus training runs spread over the year.
E1 - External API, small model (REFERENCE ONLY, excluded) |  |  |  | yes | no (provider can retire it) | Excluded by the data constraint: tickets never leave Keelpay's cloud. Shown to price the constraint.
E2 - External API, large model (REFERENCE ONLY, excluded) |  |  |  | yes | no (provider can retire it) | Same, large model.
BREAK-EVEN
API cost per ticket, small model (E1)
Volume above which self-hosting D costs less than E1 | tickets / month
... as a multiple of our volume
Reading: the data constraint (README) removes E, so the real comparison is A, B, C and D inside our cloud. With scale-to-zero hosting (billed per second, as in the Museum Guide demo) all four cost tens of euros a month, far below the value of accuracy (one point of routing accuracy is worth about EUR 14k a year in hand-overs). So cost does not decide: D must win on the gold set (accuracy on urgent tickets, valid JSON, latency). E is shown only to price the constraint: a few tens of euros a month, so the constraint costs almost nothing and is cheap insurance for tickets that carry payment data.

## Upside
02_sizing — your agent · Upside (bottom-up tree per category, year 1)
All cells are formulas linked to Inputs (green = link to another sheet). Read each block top to bottom: it is the tree from the S2 slides, per ticket category.
Line | Unit | Low | Base | High | How it is computed
Year-1 adoption factor (average of the four quarters) |  |  |  |  | → AVERAGE(Inputs ramp Q1..Q4)
Tickets per month in this category | tickets |  |  |  | → tickets/month × share
Automatable tickets per month | tickets |  |  |  | × automatable share
Deflected per month at steady state (if in scope) | tickets |  |  |  | × deflection realised × include flag
Deflected in year 1, with the adoption ramp | tickets / yr |  |  |  | × 12 × year-1 adoption factor
Gross value — human work avoided | € / yr |  |  |  | × fully loaded cost of a human ticket
Expected cost of wrong answers | € / yr |  |  |  | deflected × error rate × cost of one wrong answer — the tail, priced
AI handling cost (tokens, retries) | € / yr |  |  |  | deflected × cost per conversation × retry overhead
Net contribution of this category | € / yr |  |  |  | gross − error cost − AI cost
Tickets per month in this category | tickets |  |  |  | → tickets/month × share
Automatable tickets per month | tickets |  |  |  | × automatable share
Deflected per month at steady state (if in scope) | tickets |  |  |  | × deflection realised × include flag
Deflected in year 1, with the adoption ramp | tickets / yr |  |  |  | × 12 × year-1 adoption factor
Gross value — human work avoided | € / yr |  |  |  | × fully loaded cost of a human ticket
Expected cost of wrong answers | € / yr |  |  |  | deflected × error rate × cost of one wrong answer — the tail, priced
AI handling cost (tokens, retries) | € / yr |  |  |  | deflected × cost per conversation × retry overhead
Net contribution of this category | € / yr |  |  |  | gross − error cost − AI cost
Tickets per month in this category | tickets |  |  |  | → tickets/month × share
Automatable tickets per month | tickets |  |  |  | × automatable share
Deflected per month at steady state (if in scope) | tickets |  |  |  | × deflection realised × include flag
Deflected in year 1, with the adoption ramp | tickets / yr |  |  |  | × 12 × year-1 adoption factor
Gross value — human work avoided | € / yr |  |  |  | × fully loaded cost of a human ticket
Expected cost of wrong answers | € / yr |  |  |  | deflected × error rate × cost of one wrong answer — the tail, priced
AI handling cost (tokens, retries) | € / yr |  |  |  | deflected × cost per conversation × retry overhead
Net contribution of this category | € / yr |  |  |  | gross − error cost − AI cost
TOTALS — ALL CATEGORIES IN SCOPE
Tickets deflected in year 1 | tickets / yr |  |  |  | sum of the three categories
Gross value — human work avoided | € / yr |  |  |  | sum of the three categories
Expected cost of wrong answers | € / yr |  |  |  | sum of the three categories
AI handling cost | € / yr |  |  |  | sum of the three categories
Net variable contribution (before fixed costs) | € / yr |  |  |  | sum of the three categories
Share of all tickets deflected in year 1 | share |  |  |  | sanity check: the SOM in ticket terms

## Decision
02_sizing — your agent · Costs & Decision
Three scenarios → expected value → two comparisons (do-nothing, hurdle). Green = links to Upside / Inputs; black = formulas.
Line | Unit | Low (pessimistic) | Base | High (optimistic) | How it is computed
VALUE
Net variable contribution (Upside) + other value (Inputs rows 67–68) | € / yr |  |  |  | gross − error cost − AI cost, all categories in scope
FIXED AND SEMI-FIXED COSTS
Integration, amortised | € / yr |  |  |  | one-off ÷ amortisation years
Evaluation — eval-set and graders | € / yr
Supervision — humans in the loop | € / yr |  |  |  | FTE × cost per FTE
Monitoring and on-call | € / yr
Re-evaluation at model changes | € / yr |  |  |  | changes per year × cost per change
Total fixed and semi-fixed | € / yr
NET ANNUAL VALUE AND EXPECTED VALUE
Net annual value of the project, year 1 | € / yr |  |  |  | net variable contribution − fixed costs
Scenario probability | p |  |  |  | from Inputs
Expected value (Σ p × net value) | € / yr |  |  |  | the single number — but read the three above it first
THE TWO COMPARISONS
Do-nothing: value of the current process improving on its own | € / yr |  |  |  | efficiency gain × annual tickets × cost per ticket — not zero
Next-best project (the hurdle) | € / yr |  |  |  | from Inputs
EV minus do-nothing | € / yr
EV minus hurdle | € / yr
Pessimistic case clears the hurdle?
Decision (formula — you still write the memo)
SENSITIVITY — the assumption that flips the decision
Base case, varying the total share of handling time saved (all categories). Everything else at Base; error and AI cost are per ticket handled, so they do not move.
Total time saved (share of handling time) |  | Net annual value | vs hurdle | vs do-nothing | Reading
10%
15%
20%
25%
30%
Read down the table: the time-saved share at which the reading changes is the flip point. Name it in the memo - the S4 prototype and S6 A/B must measure it.
NOT IN THE TEMPLATE - additional readings used in the memo (the formula above stays as the course defines it)
Base-case net annual value, year 1, above zero?
Expected value above zero and above the next-best project?
Base-case net value at steady-state adoption (Q4 level held for a full year) | EUR / yr |  |  |  | Variable contribution and hand-overs scaled from the year-1 average ramp to the Q4 ramp, minus fixed costs. Year 1 carries the ramp-up; later years do not.

## Build or buy
02_sizing — your agent · Build, buy or orchestrate?
Score each option from 1 (bad) to 5 (good) on each question, weight what matters to your company (weights sum to 100 %). Then write one line in the memo — “We orchestrate because…” — and the condition that would change it. See the build / buy / orchestrate slides of Session 2 (39–40).
# | Question | Weight | Build | Buy | Orchestrate | Why — one line per score that is not obvious
01 | Strategy — Is it our edge? Would a competitor buying the same tool erase our advantage? | 8% | 4 | 2 | 4 | Routing and drafting on our ledger and dispute rules are the edge; a generic vendor copilot is not.
02 | Strategy — Do we own data or know-how that no vendor has? | 12% | 5 | 2 | 5 | Ledger, dispute history and desk policies are ours.
03 | Fit & speed — Does a product already do 80 % of the job — our languages, channels, integrations? | 10% | 2 | 4 | 3 | Vendor copilots summarise and draft but do not read our ledger or route by our desk rules out of the box.
04 | Fit & speed — Must it be live in weeks, or can it take quarters? | 8% | 1 | 5 | 3 | Build takes quarters; a vendor is weeks.
05 | Fit & speed — Do we have the people to build it and to run it — evals, on-call, re-evaluation? | 8% | 2 | 4 | 3 | We have no ML-ops team; orchestrating managed pieces lowers the run burden.
06 | Money — 3-year total cost: fees per resolution or per seat vs the seven cost lines of a build | 12% | 2 | 4 | 3 | At ~25 seats a vendor is cheap; the build carries the fixed lines of the Decision tab.
07 | Money — At what volume does per-resolution pricing cost more than building? (break-even below) | 8% | 3 | 4 | 3 | See break-even below.
08 | Risk & control — Where does our data go — GDPR, residency, may the vendor train on it? | 14% | 5 | 2 | 4 | Self-hosted keeps tickets in-house; a vendor needs EU residency and a no-training DPA to match.
09 | Risk & control — Can we leave — exit clause, export of data, prompts and eval-sets? | 8% | 5 | 2 | 4 | Exit: we keep prompts, gold set and model; a vendor locks the workflow.
10 | Risk & control — Who is liable when it is wrong, and can we see why it answered — logs, evals? | 12% | 5 | 2 | 4 | Own logs and evals vs vendor black box; liability stays with Keelpay either way.
Weights must sum to 100 %
Weighted score (1–5)
| Highest weighted score |  |  |  |  | The score informs the decision; the memo makes it. If two options are within 0.3, say which condition would decide.
BREAK-EVEN — buying per resolution vs running it yourself (base case, rough)
| Vendor price per resolution |  |  | EUR / resolution |  | Per-seat pricing expressed per time-saved-equivalent ticket: 25 seats x about EUR 45 a month (guess; vendor copilots are priced per seat; template tip: Intercom Fin listed $0.99 per resolution in 2025). Recheck the vendor price.
| Tickets deflected in year 1 (base) |  |  | tickets / yr |  | from Upside
| Annual vendor fees |  |  | € / yr |  | price × resolutions
| Your own AI handling cost (tokens, retries) |  |  | € / yr |  | from Upside
| Integration (amortised) + evaluation + re-evaluation |  |  | € / yr |  | from Decision — the build-specific fixed lines
| Running it yourself — comparable cost |  |  | € / yr |  | supervision and monitoring stay in both options, so they are left out
| Buying is cheaper by |  |  | € / yr |  | negative = running it yourself is cheaper at this volume